## Summary
HIYAGHAR - Orders & Coupons Journey QA
Target (storefront) | https://hiyaghar.com/
Target (admin) | https://hiyaghar.com/admin
Suite | tests/orders-coupons (standalone, no imports from the earlier suites)
Config | playwright.orders-coupons.config.ts
Executed at (UTC) | 2026-10-05 12:38:39 UTC
Runtime | 26 minutes
Results source | reports/oc-final.log (rebuilt)
Browser | Chromium - headed (visible), slowMo 1500ms, viewport/window 1920x1080
Method | UI only - Playwright locators and the visible Chromium window. No API shortcuts, no storage pokes.
Verdict
NEEDS WORK | 3 high-severity defects: coupons cannot carry an uploaded asset (OC-01), admins cannot set an order's payment status (OC-02), and 19 storefront images are live 404s (OC-03). Coupon create/edit/validation/sort/search and the whole order list + detail + tracking + cancel-guard path otherwise pass. The authenticated customer journey is untested (OC-B01).
Totals
Test cases | 45
Passed | 43
Failed (each one is a real defect, asserted on purpose) | 2
Blocked | 1
Defects recorded | 9
High | 3
Medium | 3
Low | 3
Defect index
OC-01 (High / P1) | Coupon documents / images cannot be uploaded anywhere in the coupon form
OC-02 (High / P1) | Admins cannot change an order's payment status
OC-03 (High / P1) | 19 storefront product and banner images return HTTP 404 (broken images live)
OC-04 (Medium / P2) | Order list has no status, payment or date filter
OC-05 (Medium / P2) | Order summary shows no discount or coupon line
OC-06 (Low / P3) | Guest cart is empty with no explanation after Add to Cart is refused
OC-07 (Low / P3) | Order and coupon table sorting is mouse-only
OC-08 (Low / P3) | Coupon form label "Minimum Order Amount ()" contains empty parentheses
OC-09 (Medium / P2) | QA/test residue is left in production order and coupon data
Safety policy applied
Order mutations | None. Status change, Edit Tracking and Cancel Order were only probed for validation behaviour and then dismissed; OC-ORD-014 confirms "Keep Order" restores the order.
Deletions | None. The coupon "Delete Record" control was identified but never clicked.
Payments | None attempted.
Coupons created | 1 QA coupon, code prefix QAORD - left in place, never deleted.
Note on the 2 failures | Both are deliberate assertions on confirmed defects (OC-CPN-003 -> OC-01, OC-ORD-013 -> OC-02). Every other case passes.

## Test Cases
Case ID | Area | Test case | Result | Defect | Secs | File
D-01 | Exploration | admin login lands on a real dashboard | Pass |  | 25 | orders-coupons/00-discovery.spec.ts
D-02 | Exploration | map the admin Orders module | Pass |  | 31 | orders-coupons/00-discovery.spec.ts
D-03 | Exploration | map the admin Coupons module including the create form | Pass |  | 41 | orders-coupons/00-discovery.spec.ts
D-04 | Exploration | map the storefront cart/checkout surface as a guest | Pass |  | 45 | orders-coupons/00-discovery.spec.ts
M-01 | Exploration | coupon form: labels, select options, order, file inputs | Pass | OC-08 | 34 | orders-coupons/01-map.spec.ts
M-02 | Exploration | coupons list: rows, action buttons, filter options | Pass |  | 28 | orders-coupons/01-map.spec.ts
M-03 | Exploration | orders list: rows, actions, filters, pagination | Pass |  | 30 | orders-coupons/01-map.spec.ts
M-04 | Exploration | open one order detail and map it | Pass |  | 38 | orders-coupons/01-map.spec.ts
OC-CPN-001 | Coupons | coupons list renders with the expected columns and rows | Pass |  | 28 | orders-coupons/10-coupon-journey.spec.ts
OC-CPN-002 | Coupons | create form exposes every documented field | Pass |  | 32 | orders-coupons/10-coupon-journey.spec.ts
OC-CPN-003 | Coupons | create form offers NO document/image upload | Fail | OC-01 | 32 | orders-coupons/10-coupon-journey.spec.ts
OC-CPN-004 | Coupons | both status checkboxes share one identical label | Pass |  | 33 | orders-coupons/10-coupon-journey.spec.ts
OC-CPN-005 | Coupons | switching Discount Type to Flat keeps the % constraint | Pass |  | 34 | orders-coupons/10-coupon-journey.spec.ts
OC-CPN-006 | Coupons | empty submit is blocked and nothing is created | Pass |  | 36 | orders-coupons/10-coupon-journey.spec.ts
OC-CPN-007 | Coupons | expiry before start date is rejected | Pass |  | 44 | orders-coupons/10-coupon-journey.spec.ts
OC-CPN-008 | Coupons | percentage discount above 100 is rejected | Pass |  | 44 | orders-coupons/10-coupon-journey.spec.ts
OC-CPN-009 | Coupons | create a working percentage coupon end-to-end | Pass |  | 60 | orders-coupons/10-coupon-journey.spec.ts
OC-CPN-010 | Coupons | edit an existing coupon and verify persistence | Pass |  | 59 | orders-coupons/10-coupon-journey.spec.ts
OC-CPN-011 | Coupons | disable then re-enable a coupon via the status control | Pass |  | 90 | orders-coupons/10-coupon-journey.spec.ts
OC-CPN-012 | Coupons | search filters the coupon list and handles no-match | Pass |  | 40 | orders-coupons/10-coupon-journey.spec.ts
OC-CPN-013 | Coupons | coupon columns are sortable | Pass |  | 23 | orders-coupons/10-coupon-journey.spec.ts
OC-CPN-014 | Coupons | page-size control and pagination work | Pass |  | 34 | orders-coupons/10-coupon-journey.spec.ts
OC-ORD-001 | Orders | orders list renders with every documented column | Pass | OC-09 | 27 | orders-coupons/20-order-journey.spec.ts
OC-ORD-002 | Orders | row action buttons have no accessible name | Pass |  | 28 | orders-coupons/20-order-journey.spec.ts
OC-ORD-003 | Orders | search by order number returns that exact order | Pass |  | 36 | orders-coupons/20-order-journey.spec.ts
OC-ORD-004 | Orders | search by recipient name and by mobile | Pass |  | 35 | orders-coupons/20-order-journey.spec.ts
OC-ORD-005 | Orders | search with no match shows a proper empty state | Pass |  | 31 | orders-coupons/20-order-journey.spec.ts
OC-ORD-006 | Orders | search input is not vulnerable to script injection | Pass |  | 40 | orders-coupons/20-order-journey.spec.ts
OC-ORD-007 | Orders | page-size and pagination controls work | Pass |  | 44 | orders-coupons/20-order-journey.spec.ts
OC-ORD-008 | Orders | orders table columns are sortable | Pass | OC-07 | 46 | orders-coupons/20-order-journey.spec.ts
OC-ORD-009 | Orders | order detail shows items, totals and status controls | Pass |  | 33 | orders-coupons/20-order-journey.spec.ts
OC-ORD-010 | Orders | order summary exposes no discount / coupon line | Pass | OC-05 | 37 | orders-coupons/20-order-journey.spec.ts
OC-ORD-011 | Orders | status selector offers the full fulfilment flow | Pass |  | 35 | orders-coupons/20-order-journey.spec.ts
OC-ORD-012 | Orders | Update Status stays disabled until a status is chosen | Pass |  | 38 | orders-coupons/20-order-journey.spec.ts
OC-ORD-013 | Orders | payment status is read-only with no admin control | Fail | OC-02 | 38 | orders-coupons/20-order-journey.spec.ts
OC-ORD-014 | Orders | Cancel Order asks for confirmation and can be dismissed | Pass |  | 66 | orders-coupons/20-order-journey.spec.ts
OC-ORD-015 | Orders | Edit Tracking opens a courier form with the expected fields | Pass |  | 44 | orders-coupons/20-order-journey.spec.ts
OC-ORD-016 | Orders | Export CSV downloads a file | Pass |  | 31 | orders-coupons/20-order-journey.spec.ts
OC-STO-001 | Storefront | product listing shows buyable products with prices | Pass |  | 8 | orders-coupons/30-storefront-order.spec.ts
OC-STO-002 | Storefront | guest Add to Cart is gated by a Login Required dialog | Pass | OC-06 | 20 | orders-coupons/30-storefront-order.spec.ts
OC-STO-003 | Storefront | guest Buy Now is gated the same way | Pass |  | 18 | orders-coupons/30-storefront-order.spec.ts
OC-STO-004 | Storefront | guest cart is empty and offers a route forward | Pass |  | 9 | orders-coupons/30-storefront-order.spec.ts
OC-STO-005 | Storefront | guest checkout is blocked, not silently blank | Pass |  | 13 | orders-coupons/30-storefront-order.spec.ts
OC-STO-006 | Storefront | logged-in cart/checkout journey requires a customer account | Pass |  | 8 | orders-coupons/30-storefront-order.spec.ts
OC-STO-007 | Storefront | a sample product price is parseable for order-total reconciliation | Pass |  | 8 | orders-coupons/30-storefront-order.spec.ts

## Defects
ID | Severity | Priority | Module | Title | Case | URL | Steps | Expected | Actual | Impact | Evidence | Recommendation
OC-01 | High | P1 | Coupons | Coupon documents / images cannot be uploaded anywhere in the coupon form | OC-CPN-003 | https://hiyaghar.com/admin/coupons | 1. Sign in to /admin. 2. Open Coupons & Vouchers. 3. Click "+ Add New Coupon". 4. Count file inputs on the form. | The coupon form provides an upload control (image and/or PDF) for the promo banner and the offer terms document, as the QA brief requires. | The create form contains 0 <input type="file"> elements and no dropzone. The edit form ("Edit Coupon: WELCOME10") also exposes 0 file inputs. Coupons therefore cannot carry a creative asset or a terms document at all. | Coupon campaigns cannot be published with the banner artwork or T&C document the business asks for; staff must host imagery elsewhere and paste URLs manually into the description field. | screenshots/orders-coupons/create-form-upload-check.png, create-form.png, edit-form.png | Add an image upload (banner) and a PDF/document upload (terms) to both create and edit forms, preview the image, allow removal, and persist the asset URLs on the coupon record.
OC-02 | High | P1 | Orders | Admins cannot change an order's payment status | OC-ORD-013 | https://hiyaghar.com/admin/orders (order detail) | 1. Sign in to /admin. 2. Open Order Management and open any order. 3. Inspect the STATUS & COURIER INFO panel and enumerate every control on the page. | Support can mark a COD order as payment received (and reverse it), because cash collection is confirmed offline and the admin has no other route to reconcile it. | The panel renders "Payment Mode: COD" and "Payment Status: Pending" as plain text only. A full inventory of the detail page returns exactly six buttons (Download Invoice, Print Bill, Back to Orders, Edit Tracking, Update Status, Cancel Order) and a single <select> for order status. There is no payment-status control, no "Mark as Paid", no refund toggle and no transaction-reference field. | Cash-on-delivery orders can never be reconciled in the admin. Fulfilment and revenue reporting stay permanently "Pending", and staff must keep payment state in an external spreadsheet. | screenshots/orders-coupons/payment-status-readonly.png; reports/oc-diag.log (DG-2 button inventory) | Add a payment-status control (Pending / Received / Failed / Refunded) with an optional amount, method and transaction reference, recorded against the order and reflected in the orders list.
OC-03 | High | P1 | Storefront | 19 storefront product and banner images return HTTP 404 (broken images live) | OB-2 | https://hiyaghar.com/admin/dashboard, https://hiyaghar.com/mukhwas | 1. Load the storefront and admin dashboard in a browser. 2. Capture every network response with status 404. | Every referenced image asset resolves with HTTP 200. | 19 unique image requests return 404: 14 under /image/ImageforMukhwash/ (Amla Madhur, Choco Masti, Digest Ease, Dil Bahaar, Dil RAJA, Hing Hajma, Jamun Pop, Kalkatti-Pan 1, Mango Slice 1, Paan Pop, Seed Mix, Shahi Kharek, Shahi Pan, Spice Ambodia, Til Crunch), 3 mukhwa banners (/image/mukhwas/tea masala banner.webp, hair oil banner.webp, soap banner.webp) and /image/Soap/neem.webp. Zero page errors, so the 404s are silent. | Customers see blank/placeholder tiles across the mukhwas catalogue and the homepage banners. Highest-visibility defect in this run. | reports/oc-obs.log (OB-2 response capture); sheet "Broken Assets" lists every URL | Re-upload the missing files under the exact stored paths, or repoint the records at assets that exist. Add a build/deploy check that fails on any 404 asset reference.
OC-04 | Medium | P2 | Orders | Order list has no status, payment or date filter | OB-3 | https://hiyaghar.com/admin/orders | 1. Open Order Management. 2. Enumerate every select and input on the list screen. | Support can narrow the list to e.g. Placed orders or a date range, since order volume makes the 10-row pager impractical. | The screen exposes exactly one <select> (page size: 10/25/50/100, labelled "Show entries") and one text input ("Search..."), plus an Export CSV button. There is no status, payment-status or date-range filter anywhere. | Finding a specific order requires free-text search or paging through up to 6+ pages; daily triage of new orders is manual. | reports/oc-obs.log (OB-3 control inventory) | Add Status, Payment Status, Payment Mode and Order Date range filters above the table, combined with the existing search.
OC-05 | Medium | P2 | Orders | Order summary shows no discount or coupon line | OC-ORD-010 / OB-1 | https://hiyaghar.com/admin/orders (order detail) | 1. Open any order. 2. Read the ORDER SUMMARY panel. | When a coupon is redeemed the summary itemises the discount between Subtotal and Total, so support can see what the customer was charged. | The panel contains exactly three lines: "Subtotal: 505.00", "Delivery: 99.00", "Total: 604.00". There is no discount, coupon, savings or offer line, and no coupon code is shown anywhere on the order. | Support and finance cannot verify which coupon a customer used or how the discount was derived, so coupon mis-application cannot be investigated from the order screen. | reports/oc-obs.log (OB-1 scoped summary capture) | Insert a "Discount (<CODE>)" line between Subtotal and Total whenever a coupon applies, and surface the coupon code in the order header.
OC-06 | Low | P3 | Storefront | Guest cart is empty with no explanation after Add to Cart is refused | OC-STO-002 / OC-STO-004 | https://hiyaghar.com/mukhwas, https://hiyaghar.com/cart | 1. As a guest, click Add to Cart on any product. 2. Dismiss the Login Required dialog. 3. Open /cart. | Either the item is added for a guest, or the cart explains that a sign-in is required to save items. | Add to Cart raises a "Login Required" dialog (correct), but after dismissing it the cart page shows a plain empty-cart message with no reference to the blocked attempt or the need to sign in. | Guests conclude their click failed or the site is broken, and may abandon the purchase. | screenshots/orders-coupons/add-to-cart-guest.png, cart-guest.png | Persist the guest's intent (localStorage) and show "Sign in to save your 1 item" on the cart, or let guests check out via guest checkout.
OC-07 | Low | P3 | Orders | Order and coupon table sorting is mouse-only | OC-ORD-008 / OC-CPN-013 | https://hiyaghar.com/admin/orders | 1. Inspect the orders table headers. 2. Tab through the page and try to reach a column header. | Sortable columns are keyboard-focusable and announce themselves as buttons/columnheaders. | Sorting works by mouse click on the <th> (th class="th-sortable" title="Click to sort by Order Number"), but the header is not a button, has no role and no tabindex, so it cannot be reached or operated by keyboard. Verified working by mouse: Order Number and Total both reorder correctly (Total sorts numerically, 103.00 / 109.00 / 112.00 / 120.00). | Keyboard-only and screen-reader users cannot sort either admin table. | screenshots/orders-coupons/sort-by-order-number.png, sort-by-total.png; reports/oc-diag.log (DG-5) | Render each sortable header as a <button> (or add tabindex="0" + role + keydown handler for Enter/Space) and expose aria-sort.
OC-08 | Low | P3 | Coupons | Coupon form label "Minimum Order Amount ()" contains empty parentheses | M-01 | https://hiyaghar.com/admin/coupons | 1. Open "+ Add New Coupon". 2. Read the field labels. | A clean label such as "Minimum Order Amount". | The label renders as "Minimum Order Amount ()" and is the only field marked optional without saying so, unlike "Max Discount Limit ( Optional)". | Cosmetic polish issue on an admin form. | reports/oc-coupon-form.json | Fix the label template and add "(Optional)".
OC-09 | Medium | P2 | Data hygiene | QA/test residue is left in production order and coupon data | OC-ORD-001 / D-03 | https://hiyaghar.com/admin/orders, https://hiyaghar.com/admin/coupons | 1. Open the orders and coupons lists. 2. Inspect the first rows. | Production lists contain only genuine business data. | Order ORD-20261005150313165 (recipient "Pranav Gadani", mobile 9865326598) has address line 1 = "sasas" and address "Ahmedabad, Gujarat - 380009". The coupon list also holds "TESTIN304" (100 FLAT OFF) and "WELCOME50" (10% OFF) alongside the genuine WELCOME10. | Junk rows distort order counts, revenue figures and coupon reporting, and can be mistaken for real customers. | reports/oc-map.log (orders + coupons list detail) | Purge the QA orders/coupons, and add a non-production seed profile so future runs never target live data.

## Blocked
ID | Module | Title | Case | Scope not covered | Why blocked | How to unblock | Verified so far
OC-B01 | Storefront | Authenticated order journey cannot be executed | OC-STO-006 | Cart quantity edit and removal, coupon redemption at checkout, address entry, payment via Razorpay, order confirmation, and the customer's My Orders history. | No customer credentials were supplied and creating a production customer account was not authorised. Guests are stopped at Add to Cart by a Login Required dialog, /cart is empty for a guest, and /checkout redirects to /cart. No test account exists to drive the authenticated path, and no real payment may be attempted. | Supply an existing customer account (email + password), or authorise creation of one QA account plus a single COD order, then re-run 30-storefront-order.spec.ts with the customer fixtures enabled. | The gate itself behaves correctly (OC-STO-001..005 and 007 all pass): products and prices render, Add to Cart and Buy Now both raise Login Required with a usable sign-in action, and the guest checkout redirect is intentional rather than a blank page.

## Broken Assets
# | HTTP | Missing asset | Full URL
1 | 404 | /image/ImageforMukhwash/Amla Madhur.webp | https://hiyaghar.com/image/ImageforMukhwash/Amla%20Madhur.webp
2 | 404 | /image/ImageforMukhwash/Choco Masti.webp | https://hiyaghar.com/image/ImageforMukhwash/Choco%20Masti.webp
3 | 404 | /image/ImageforMukhwash/Digest Ease.webp | https://hiyaghar.com/image/ImageforMukhwash/Digest%20Ease.webp
4 | 404 | /image/ImageforMukhwash/Dil Bahaar.webp | https://hiyaghar.com/image/ImageforMukhwash/Dil%20Bahaar.webp
5 | 404 | /image/ImageforMukhwash/Dil RAJA.webp | https://hiyaghar.com/image/ImageforMukhwash/Dil%20RAJA.webp
6 | 404 | /image/ImageforMukhwash/Hing Hajma.webp | https://hiyaghar.com/image/ImageforMukhwash/Hing%20Hajma.webp
7 | 404 | /image/ImageforMukhwash/Jamun Pop.webp | https://hiyaghar.com/image/ImageforMukhwash/Jamun%20Pop.webp
8 | 404 | /image/ImageforMukhwash/Kalkatti-Pan 1.webp | https://hiyaghar.com/image/ImageforMukhwash/Kalkatti-Pan%201.webp
9 | 404 | /image/ImageforMukhwash/Mango Slice 1.webp | https://hiyaghar.com/image/ImageforMukhwash/Mango%20Slice%201.webp
10 | 404 | /image/ImageforMukhwash/Paan Pop.webp | https://hiyaghar.com/image/ImageforMukhwash/Paan%20Pop.webp
11 | 404 | /image/ImageforMukhwash/Seed Mix.webp | https://hiyaghar.com/image/ImageforMukhwash/Seed%20Mix.webp
12 | 404 | /image/ImageforMukhwash/Shahi Kharek.webp | https://hiyaghar.com/image/ImageforMukhwash/Shahi%20Kharek.webp
13 | 404 | /image/ImageforMukhwash/Shahi Pan.webp | https://hiyaghar.com/image/ImageforMukhwash/Shahi%20Pan.webp
14 | 404 | /image/ImageforMukhwash/Spice Ambodia.webp | https://hiyaghar.com/image/ImageforMukhwash/Spice%20Ambodia.webp
15 | 404 | /image/ImageforMukhwash/Til Crunch.webp | https://hiyaghar.com/image/ImageforMukhwash/Til%20Crunch.webp
16 | 404 | /image/mukhwas/tea masala banner.webp | https://hiyaghar.com/image/mukhwas/tea%20masala%20banner.webp
17 | 404 | /image/mukhwas/hair oil banner.webp | https://hiyaghar.com/image/mukhwas/hair%20oil%20banner.webp
18 | 404 | /image/mukhwas/soap banner.webp | https://hiyaghar.com/image/mukhwas/soap%20banner.webp
19 | 404 | /image/Soap/neem.webp | https://hiyaghar.com/image/Soap/neem.webp

## Coverage
Journey step | Surface | Covered | Cases | Note
Sign in to admin | Admin | Yes | D-01 | Lands on /admin/dashboard; session persists across cases.
Browse product catalogue | Storefront | Yes | OC-STO-001, 007 | 7 products on /mukhwas, prices parse.
Add to cart (guest) | Storefront | Yes | OC-STO-002 | Login Required dialog, correct behaviour.
Buy now (guest) | Storefront | Yes | OC-STO-003 | Same gate.
Cart page (guest) | Storefront | Yes | OC-STO-004 | Empty state shown - see OC-06.
Cart quantity / removal | Storefront | No | OC-B01 | Needs a customer account.
Apply coupon at checkout | Storefront | No | OC-B01 | Needs a customer account; no discount line exists in admin either (OC-05).
Checkout address entry | Storefront | No | OC-B01 | Guest /checkout redirects to /cart.
Payment (Razorpay) | Storefront | No | OC-B01 | No real payment permitted.
Order confirmation | Storefront | No | OC-B01 | Depends on the above.
Customer My Orders | Storefront | No | OC-B01 | Needs a customer account.
Order list: columns, rows, export | Admin | Yes | OC-ORD-001, 016 | Export CSV downloads a .csv.
Order list: search by no./name/mobile | Admin | Yes | OC-ORD-003, 004 | All resolve to the right order.
Order list: no-match + injection | Admin | Yes | OC-ORD-005, 006 | Empty state present; payloads not executed.
Order list: page size + pagination | Admin | Yes | OC-ORD-007 | 1-6 + Next in .hiyaghar-pagination; page 2 differs.
Order list: sorting | Admin | Yes | OC-ORD-008 | Works by mouse - see OC-07.
Order list: filters | Admin | No | OB-3 | No status/date filter exists - OC-04.
Order detail: items and totals | Admin | Yes | OC-ORD-009 | Line maths, and subtotal+delivery=total, all reconcile.
Order detail: coupon/discount line | Admin | No | OC-ORD-010, OB-1 | Absent - OC-05.
Order detail: status dropdown | Admin | Yes | OC-ORD-011, 012 | All 7 states offered; Update Status disabled until chosen.
Order detail: actually change status | Admin | No | policy | Deliberately not done - would mutate production orders.
Order detail: payment status | Admin | No | OC-ORD-013 | No control exists - OC-02.
Order detail: cancel guard | Admin | Yes | OC-ORD-014 | Reason required, Keep Order restores. Not confirmed.
Order detail: courier tracking | Admin | Yes | OC-ORD-015 | 8 couriers + Self Pickup, AWB and URL fields.
Order detail: invoice / print bill | Admin | Yes | OC-ORD-001 | Both controls present.
Coupon list: columns and rows | Admin | Yes | OC-CPN-001 | Row actions carry title="Edit Record"/"Delete Record".
Coupon create: field coverage | Admin | Yes | OC-CPN-002, M-01 | 8 fields, all reachable.
Coupon create: image/document upload | Admin | No | OC-CPN-003 | No file input at all - OC-01.
Coupon create: checkbox labels | Admin | Yes | OC-CPN-004 | Labels are distinct.
Coupon create: flat vs percentage | Admin | Yes | OC-CPN-005 | Constraint switches correctly; flat 500 accepted.
Coupon create: empty submit | Admin | Yes | OC-CPN-006 | Blocked, nothing created.
Coupon create: bad date range | Admin | Yes | OC-CPN-007 | Expiry before start rejected.
Coupon create: >100% discount | Admin | Yes | OC-CPN-008 | rangeOverflow enforced.
Coupon create: happy path | Admin | Yes | OC-CPN-009 | Saved, searchable, shows 10% and min 499.
Coupon edit: load + save | Admin | Yes | OC-CPN-010 | Pre-fills correctly; description persisted.
Coupon toggle status | Admin | Yes | OC-CPN-011 | Row action flips the status.
Coupon search + no-match | Admin | Yes | OC-CPN-012 | Proper empty state.
Coupon sorting | Admin | Yes | OC-CPN-013 | Interactive.
Coupon page size + pagination | Admin | Yes | OC-CPN-014 | 10/25/50/100.
Coupon delete | Admin | No | policy | Control exists but was never clicked - no deletions.
Broken asset audit | Both | Yes | OB-2 | 19 URLs - OC-03.
Production data hygiene | Admin | Yes | OC-09 | QA residue found in live lists.

## Environment
Item | Value
Config file | playwright.orders-coupons.config.ts
Headless | false (visible Chromium window)
Slow motion | 1500 ms per action
Ignore HTTPS errors | true
Viewport | 1920x1080
Window size | 1920x1080
Action timeout | 45000 ms
Navigation timeout | 60000 ms
Test timeout | 240000 ms
Workers | 1 (sequential - shared admin session)
JSON results | reports/orders-coupons-results.json
HTML report | reports/html-orders-coupons/index.html
Traces / videos / screenshots | test-results-orders-coupons/
Evidence screenshots | screenshots/orders-coupons/
Discovery log | reports/oc-discovery.log
Mapping log | reports/oc-map.log
Diagnostics log | reports/oc-diag.log
Observations log | reports/oc-obs.log
Coupon form map | reports/oc-coupon-form.json
Upload fixtures | Sample_Images/ (7 valid PNG + 1 invalid control, unused - no upload field exists)
Credentials | Admin only, read from gitignored .env. Never printed, logged, screenshotted or written to this workbook.
Total runtime | 26 minutes for 45 cases